## Brainstorming
Possible Charting Options |  |  |  | Mock Up
Basic Stats by Product | Purpose of inclusion | Priority (1-high, 3-low)
average sales, etc. | shows sales breakdowns by item/mix to show what is successful, what could maybe be cut | 1 | √ |  | Revenue Ops for Used Car Sales
Sales cycle time | show how long it is taking to turn customer from prospect to client (either as static number or over time) | 1
Win rates / Conversion Rates | show ability to turn prospects into clients (static snapshot or over time) | 1
Customer acquisition cost | show cost of acquiring a single customer per marketing effort | 1 |  |  | Total Purchases | Total Opportunities | Win Rate |  | Customer Acquisition Cost | Sales Cycle Time
Recurring revenue | how much of this revenue can be relied upon regularly | 2
CLV | how much can we expect to get from each customer in their relationship with us (this may have to be foregone this time due to data limitations on length of relationships) | 2 |  |  | ### | ### | %%% |  | $$$ | ### days
Customer churn | Measure customer retention during a certain timeframe (perhaps after product launch, etc.) | 2
Renewal percentage/amounts | Measure customer retention during a certain timeframe (perhaps after product launch, etc.) | 3 |  |  | Filter:
Unique users | Interesting for service like Netflix, etc. where multiple people could be leveraging same customer id, etc. | 3 |  |  | Car Make | Car Model | Car Year
Active users | How many actively using the service | 3
New users | New customers over time | 2
Sales Metrics
Customer funnel & follow-through (https://plotly.com/python/funnel-charts/) | Find where dropoff may be happening with customers in the acquisition pipeline and address that area of the business | 2
A/B Test results? If time? | Possible dashboard "extra" showing a/b test results of a marketing/UI/UX effort | 3 |  |  | Sales by Make/Model/Yr (dynamic) |  |  | YoY Sales
Market Benchmarking by product | (could possibly be service within product? Only share data with those that opt in - more buy-in = more information)
Quartiles by product | Show where your product is ranking compared to peers, if value is aligning with price | 1 | √
Product tiers & price range consolidation | See which tiers/product categories of offerings are aligned with peers (! anecdotal finance example @ $1M, 1%) | 1 | √
Prediction modeling (start w/ simple ARIMA, etc.) |  |  |  |  | Recurring Revenue by Revenue Stream
show ranges | Show possible future modeling, with 90% confidence interval expectations | 1
Forecast accuracy | Show how accurate past models have been, and whether they can be trusted | 2
Income Statement
Margins over time | See where price compression is happening, especially in relation to expenses for those products | 2
Accts receivable (billed amounts) / Accts payable (invested amounts) | See what is not yet in the income statement but can be accounted for | 2
Cost of Revenue/Sales | Self-explanatory | 2 |  |  | Sales Lifecycle
Revenue streams (https://plotly.com/python/funnel-charts/) | Show different revenue streams/channels as a percentage of overall revenue, over time | 1
Cash flow (https://plotly.com/python/sankey-diagram/) | Show where revenue is going, if price increases are necessary or expense cuts are necessary | 1 |  |  | Customer Acquisition Cost over Time |  |  | Customer Lifetime Value
[5 empty] | Customer Churn over time |  |  | Customer Funnel
Competitor Analysis
[5 empty] | Product Tier / Price Consolidation Analysis |  |  | Per-Product Analysis

## Decision Log
Decision Log
Potential Solution | Problem | Details | Impacts | Decision Date | Implementation | Result/Evaluation | Notes
Leverage Dash/Plotly | Time constraints | Leverage basic Dash/Plotly combination to build dashboard as it is fresher in my brain and would involve less review in the time remaining | May result in less impressive visuals in order to achieve a minimum viable product | 2023-05-14 | Began leveraging a simple Dash framework to get started, will expand as time allows.
Change to "used car sales" instead of just regular car sales | Mockaroo opportunity | Mockaroo allows for a year selection in the car fields | This will allow for more opportunities to break down the data later | 2023-05-14 | Added field | I regret this decision. It hasn't offered much insight and instead made the charts messier | I will likely remove this in future iterations.
Separate "account"/"purchase" vs "opportunity" datasets | Mockaroo Limitations | Limited in ability to manipulate mock datasets, so will separate opportunities from actual purchases. | Minimal - extra code that would otherwise not be required | 2023-05-14 | Implemented code at onset of main app py file to merge datasets
Include chart codes in `app.layout` | Charts not properly rendering | Originally tried to condense code to include line in `app.layout` that had final line of "html.Div(id='outputDiv', children=[])" drawing from a function, but charts would not render. | Code will be less concise, and (I find) less readable | 2023-05-14 | Instead of keeping code clean and implementing chart code at the bottom of the code in a way that also was able to include more functions in the chart_functions.py file, creating a cleaner code, I moved a more lengthy code to the initial app.layout call | Looks way more clunky and less easy to read, but did finally render. | Will work on fixing this in future iterations.
"Quarter over Quarter Sales" | Data only goes back 6 months in "purchases" | Data limited, no time to redo to include enough to do YoY or trailing 6 months, etc. | Chart looks a little silly with only 3 data points | 2023-05-14 | Used QoQ sales | Not as telling, but probably would not have provided much more information on a sample dataset anyway.
Forego modeling options | Time constraints | Would really like to do at least one forecasting model with ARIMA, but simply running out of time. In practice, would look at multiple modeling types for time series and see which ones tend to be more accurate - or even give a dropdown of options for a client to choose which one fits their business the best. | Reduces information gain on dashboard - not as powerful | 2023-05-15 | - | Missing what I think is a very important and interesting piece of information | Will work on adding this in future iterations.
Reduce importance of CLV inclusion from 1 to 2 | Time constraints, Data constraints | Data limited to six months, very individualized, so going to be difficult to find recurrences of data to track something like this, especially over an extended period of time to get an accurate reading on CLV. | Reduces information gain on dashboard - not as powerful | 2023-05-15 | - | Missing what I think is a very important and interesting piece of information | Will work on adding this in future iterations.
Reduce importance of customer funnel inclusion from 1 to 2 | Time constraints, Data constraints | Data does not include multiple steps, only "opportunity", "purchase", at this time. Also, running out of itme | Reduces information gain on dashboard - not as powerful | 2023-05-15 | - | Missing what I think is a very important and interesting piece of information | Will work on adding this in future iterations.
Reduce importance of revenue stream, cash flow inclusion from 1 to 2 | Time constraints, Data constraints | Data does not include income statement pieces at this time, running out of timet o include them | Reduces information gain on dashboard - not as powerful | 2023-05-15 | - | Missing what I think is a very important and interesting piece of information | Will work on adding this in future iterations.
Forego unit tests | Time constraints | I really hate this decision. Given the fact that I created the data with Mockeroo, I am less concerned about | Possibility of dirty data getting through | 2023-05-16 | - | Profound regret. | One of the first things I will add in future iterations.
Run the code locally on development server | Time constraints | Would prefer to use Dash Tools/Render to deploy the dashboard, but running out of time to set that up | Requires repo download to run code | 2023-05-16 | Leave as-is, update readme to include instructions for launching local development server | It works, but it fills me with sadness and woe. | Will also update as soon as time allows.
Add Tabs | Dashboard is getting overwhelming | Break up the sections by using tabs instead | Keeps individual tab dashboards smaller and more concise to their purpose | 2023-05-16 | Tab code within `app.layout` and some refactoring of certain areas to accommodate it | Looks much cleaner | Will still require some layout reformatting
Expand dataset | Mockaroo Constraints | Expanding dataset by pulling from Mockaroo in batches of ~1000 at a time, up to 5000 per dataset, writing code to collate data subsets into larger dataset. | Will allow for YoY data, more repetative data for hopefully further insights | 2023-05-17 | Included a code-cleaning .py file. As it is just run the once to generate, clean, and wrangle datasets, it does not get a __main__ function and just exists for single-use runs. | Significantly increased the dataset options, helped provide better data insights in granular data, but also created some version of CLT where, since the data is randomly generated, it all sort of merges to similar means/numbers.
Calculate win rate as 6M purchases / TTM opportunities | Dataset does not define "closing" of opportunities | Since we do not define the close of an opportunity here, we will just use total purchases in the last 6 months, over TTM opportunity counts. | Reduces accuracy of win rate, but since I batched the data by year to avoid purchase/opportunity date overlap, it should be somewhat reflective. | 2023-05-17 | Reducing datasets to 6m/ttm in `chart_functions.py`, respectively. Recalculating based on those values. | Not as precise as I would like, but it works.
Forego slider on Sankey chart | Callbacks not cooperating within other callbacks | Was intending to put a slider for QoQ comparison on the Sankey Chart (Financial Analysis), but I could either get the slider to render, or the chart, but not both and not leveraging callbacks correctly. | Static chart does not allow for comparisons, unfortunately | 2023-05-17 | Commenting out code and refactoring only to include static - will leave code in the codebase in case I want to try again later | Less dynamic
Just set a random ARIMA pdq | Time constraints | Not enough time to do an entire "optimal prediction" model research tool, and since accurate predictions on fake data is not the point of the exercise, I will just assign a random PDQ to the model and work with it. | Inaccurate predictions, but data is random anyway so not particularly impactful. | 2023-05-18 | Will just do standard ARIMA with (1,0,12) | Extreme predictions
Leave competitor pricing delta list as-is | Time constraints | The competitor pricing delta list currently is topped by low-sales items - in theory, would possibly eliminate any low-sales items, but wil leave for now | List is less meaningful, as quantity of products would be low to make pricing impact | 2023-05-18 | Leave out any additional filtering for now
Sort competitor table by opportunity cost | Fixing previous line | Instead of trying to finagle filtering, will instead calculate and sort by opportunity costs | Better shows areas where pricing improvements may have material impact | 2023-05-18 | Change code to sort by opportunity cost | More material/impactful results
Forego win rate strip chart | Time constraints | Win rate strip chart getting too messy to break down by make/model. Groupbys becoming extremely time consuming. Will forego for now | Missing chart | 2023-05-18
Host on Render | Heroku no longer free | Heroku is no longer free, there is a free service called Render for Dash apps | Service will be slower | 2023-05-19 | Deployed on Render successfully | Slow chart generatin