## Brainstorming
Possible Charting Options
Basic Stats by Product
average sales, etc.
Sales cycle time
Win rates
Customer acquisition cost
Recurring revenue
CLV
Market Benchmarking by product
quartiles/tiers
Prediction modeling (start w/ simple ARIMA, etc.)
show ranges

## Decision Log
Decision Log
Potential Solution | Problem | Details | Impacts | Decision Date | Implementation | Result/Evaluation | Notes
Leverage Dash/Plotly | Time constraints | Leverage basic Dash/Plotly combination to build dashboard as it is fresher in my brain and would involve less review in the time remaining | May result in less impressive visuals in order to achieve a minimum viable product | 2023-05-13 | Began leveraging a simple Dash framework to get started, will expand as time allows.
Separate "account"/"purchase" vs "opportunity" datasets | Mockaroo Limitations | Limited in ability to manipulate mock datasets, so will separate opportunities from actual purchases. | Minimal - extra code that would otherwise not be required | 2023-05-13 | Implemented code at onset of main app py file to merge datasets
Include chart codes in `app.layout` | Charts not properly rendering | Originally tried to condense code to include line in `app.layout` that had final line of "html.Div(id='outputDiv', children=[])" drawing from a function, but charts would not render. | Code will be less concise, and (I find) less readable | 2023-05-14